## README
Day 2 — Laycan Matrix | Researcher 2 — Domain
Purpose | Define planning laycan windows for every vessel-route pair in the 30-day Alpha horizon.
Planning horizon | 05-Sep-2026 to 04-Oct-2026 (30 calendar days).
Laycan definition | A 3-day planning window in which the vessel may be considered ready to load on the route.
Important | These are synthetic/Alpha scheduling assumptions, not real-time charter availability or actual fixture dates.
Feasibility rule | A vessel-route assignment is feasible only when vessel DWT >= route planning cargo.
Solver use | Feasible rows may be considered by the MILP. Infeasible rows should be forced to zero / forbidden.
Voyage days | Recomputed as approximate nautical distance / 13 knots. Port waiting, weather and canal delays are excluded.
Why 3 days? | A small laycan window gives the solver a meaningful scheduling choice without overcomplicating Alpha.
Next handoff | Tech Lead 2 should use Laycan Start/End to build Big-M/time feasibility constraints.

## Day2_Laycan_Matrix
Vessel ID | Real Vessel Name | Route ID | Origin Port | Destination Port | Cargo | Planning Cargo (MT) | Vessel DWT (MT) | Laycan Start | Laycan End | Laycan Days | Feasible? | Feasibility Reason | Voyage Days (Planning) | 30-Day Horizon Check | Big-M Constraint Use | Domain Note
V-001 | MV TS INDEX | R-01 | Hay Point | Visakhapatnam | Coking coal | 50000 | 38854 | 2026-09-05 | 2026-09-07 | 3 | NO | Vessel DWT 38,854 MT is below planning cargo 50,000 MT. | 361.5 | YES | FORBID (set assignment upper bound to 0) | Infeasible in Alpha because cargo exceeds vessel DWT; keep row for explicit solver filtering.
V-002 | MV LOFTY MOUNTAIN | R-01 | Hay Point | Visakhapatnam | Coking coal | 50000 | 51008 | 2026-09-06 | 2026-09-08 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 361.5 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-003 | MV IMPERIAL FORTUNE | R-01 | Hay Point | Visakhapatnam | Coking coal | 50000 | 53505 | 2026-09-07 | 2026-09-09 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 361.5 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-004 | MV VIENNA WOOD N | R-01 | Hay Point | Visakhapatnam | Coking coal | 50000 | 55768 | 2026-09-08 | 2026-09-10 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 361.5 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-005 | MV NORTH QUAY | R-01 | Hay Point | Visakhapatnam | Coking coal | 50000 | 57016 | 2026-09-05 | 2026-09-07 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 361.5 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-001 | MV TS INDEX | R-02 | Hay Point | Paradip | Coking coal | 50000 | 38854 | 2026-09-07 | 2026-09-09 | 3 | NO | Vessel DWT 38,854 MT is below planning cargo 50,000 MT. | 346.2 | YES | FORBID (set assignment upper bound to 0) | Infeasible in Alpha because cargo exceeds vessel DWT; keep row for explicit solver filtering.
V-002 | MV LOFTY MOUNTAIN | R-02 | Hay Point | Paradip | Coking coal | 50000 | 51008 | 2026-09-08 | 2026-09-10 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 346.2 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-003 | MV IMPERIAL FORTUNE | R-02 | Hay Point | Paradip | Coking coal | 50000 | 53505 | 2026-09-09 | 2026-09-11 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 346.2 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-004 | MV VIENNA WOOD N | R-02 | Hay Point | Paradip | Coking coal | 50000 | 55768 | 2026-09-10 | 2026-09-12 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 346.2 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-005 | MV NORTH QUAY | R-02 | Hay Point | Paradip | Coking coal | 50000 | 57016 | 2026-09-07 | 2026-09-09 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 346.2 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-001 | MV TS INDEX | R-03 | Hay Point | Haldia | Coking coal | 40000 | 38854 | 2026-09-09 | 2026-09-11 | 3 | NO | Vessel DWT 38,854 MT is below planning cargo 40,000 MT. | 353.8 | YES | FORBID (set assignment upper bound to 0) | Infeasible in Alpha because cargo exceeds vessel DWT; keep row for explicit solver filtering.
V-002 | MV LOFTY MOUNTAIN | R-03 | Hay Point | Haldia | Coking coal | 40000 | 51008 | 2026-09-10 | 2026-09-12 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 353.8 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-003 | MV IMPERIAL FORTUNE | R-03 | Hay Point | Haldia | Coking coal | 40000 | 53505 | 2026-09-11 | 2026-09-13 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 353.8 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-004 | MV VIENNA WOOD N | R-03 | Hay Point | Haldia | Coking coal | 40000 | 55768 | 2026-09-12 | 2026-09-14 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 353.8 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-005 | MV NORTH QUAY | R-03 | Hay Point | Haldia | Coking coal | 40000 | 57016 | 2026-09-09 | 2026-09-11 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 353.8 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-001 | MV TS INDEX | R-04 | Hay Point | Gangavaram | Coking coal | 50000 | 38854 | 2026-09-11 | 2026-09-13 | 3 | NO | Vessel DWT 38,854 MT is below planning cargo 50,000 MT. | 369.2 | YES | FORBID (set assignment upper bound to 0) | Infeasible in Alpha because cargo exceeds vessel DWT; keep row for explicit solver filtering.
V-002 | MV LOFTY MOUNTAIN | R-04 | Hay Point | Gangavaram | Coking coal | 50000 | 51008 | 2026-09-12 | 2026-09-14 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 369.2 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-003 | MV IMPERIAL FORTUNE | R-04 | Hay Point | Gangavaram | Coking coal | 50000 | 53505 | 2026-09-13 | 2026-09-15 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 369.2 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-004 | MV VIENNA WOOD N | R-04 | Hay Point | Gangavaram | Coking coal | 50000 | 55768 | 2026-09-14 | 2026-09-16 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 369.2 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-005 | MV NORTH QUAY | R-04 | Hay Point | Gangavaram | Coking coal | 50000 | 57016 | 2026-09-11 | 2026-09-13 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 369.2 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-001 | MV TS INDEX | R-05 | Gladstone | Visakhapatnam | Coking coal | 50000 | 38854 | 2026-09-13 | 2026-09-15 | 3 | NO | Vessel DWT 38,854 MT is below planning cargo 50,000 MT. | 369.2 | YES | FORBID (set assignment upper bound to 0) | Infeasible in Alpha because cargo exceeds vessel DWT; keep row for explicit solver filtering.
V-002 | MV LOFTY MOUNTAIN | R-05 | Gladstone | Visakhapatnam | Coking coal | 50000 | 51008 | 2026-09-14 | 2026-09-16 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 369.2 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-003 | MV IMPERIAL FORTUNE | R-05 | Gladstone | Visakhapatnam | Coking coal | 50000 | 53505 | 2026-09-15 | 2026-09-17 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 369.2 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-004 | MV VIENNA WOOD N | R-05 | Gladstone | Visakhapatnam | Coking coal | 50000 | 55768 | 2026-09-16 | 2026-09-18 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 369.2 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-005 | MV NORTH QUAY | R-05 | Gladstone | Visakhapatnam | Coking coal | 50000 | 57016 | 2026-09-13 | 2026-09-15 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 369.2 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-001 | MV TS INDEX | R-06 | Gladstone | Paradip | Coking coal | 50000 | 38854 | 2026-09-15 | 2026-09-17 | 3 | NO | Vessel DWT 38,854 MT is below planning cargo 50,000 MT. | 353.8 | YES | FORBID (set assignment upper bound to 0) | Infeasible in Alpha because cargo exceeds vessel DWT; keep row for explicit solver filtering.
V-002 | MV LOFTY MOUNTAIN | R-06 | Gladstone | Paradip | Coking coal | 50000 | 51008 | 2026-09-16 | 2026-09-18 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 353.8 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-003 | MV IMPERIAL FORTUNE | R-06 | Gladstone | Paradip | Coking coal | 50000 | 53505 | 2026-09-17 | 2026-09-19 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 353.8 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-004 | MV VIENNA WOOD N | R-06 | Gladstone | Paradip | Coking coal | 50000 | 55768 | 2026-09-18 | 2026-09-20 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 353.8 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-005 | MV NORTH QUAY | R-06 | Gladstone | Paradip | Coking coal | 50000 | 57016 | 2026-09-15 | 2026-09-17 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 353.8 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-001 | MV TS INDEX | R-07 | Gladstone | Haldia | Coking coal | 40000 | 38854 | 2026-09-17 | 2026-09-19 | 3 | NO | Vessel DWT 38,854 MT is below planning cargo 40,000 MT. | 361.5 | YES | FORBID (set assignment upper bound to 0) | Infeasible in Alpha because cargo exceeds vessel DWT; keep row for explicit solver filtering.
V-002 | MV LOFTY MOUNTAIN | R-07 | Gladstone | Haldia | Coking coal | 40000 | 51008 | 2026-09-18 | 2026-09-20 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 361.5 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-003 | MV IMPERIAL FORTUNE | R-07 | Gladstone | Haldia | Coking coal | 40000 | 53505 | 2026-09-19 | 2026-09-21 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 361.5 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-004 | MV VIENNA WOOD N | R-07 | Gladstone | Haldia | Coking coal | 40000 | 55768 | 2026-09-20 | 2026-09-22 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 361.5 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-005 | MV NORTH QUAY | R-07 | Gladstone | Haldia | Coking coal | 40000 | 57016 | 2026-09-17 | 2026-09-19 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 361.5 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-001 | MV TS INDEX | R-08 | Dalrymple Bay | Paradip | Coking coal | 50000 | 38854 | 2026-09-19 | 2026-09-21 | 3 | NO | Vessel DWT 38,854 MT is below planning cargo 50,000 MT. | 342.3 | YES | FORBID (set assignment upper bound to 0) | Infeasible in Alpha because cargo exceeds vessel DWT; keep row for explicit solver filtering.
V-002 | MV LOFTY MOUNTAIN | R-08 | Dalrymple Bay | Paradip | Coking coal | 50000 | 51008 | 2026-09-20 | 2026-09-22 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 342.3 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-003 | MV IMPERIAL FORTUNE | R-08 | Dalrymple Bay | Paradip | Coking coal | 50000 | 53505 | 2026-09-21 | 2026-09-23 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 342.3 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-004 | MV VIENNA WOOD N | R-08 | Dalrymple Bay | Paradip | Coking coal | 50000 | 55768 | 2026-09-22 | 2026-09-24 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 342.3 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-005 | MV NORTH QUAY | R-08 | Dalrymple Bay | Paradip | Coking coal | 50000 | 57016 | 2026-09-19 | 2026-09-21 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 342.3 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-001 | MV TS INDEX | R-09 | Vancouver | Visakhapatnam | Metallurgical coal | 50000 | 38854 | 2026-09-22 | 2026-09-24 | 3 | NO | Vessel DWT 38,854 MT is below planning cargo 50,000 MT. | 600 | YES | FORBID (set assignment upper bound to 0) | Infeasible in Alpha because cargo exceeds vessel DWT; keep row for explicit solver filtering.
V-002 | MV LOFTY MOUNTAIN | R-09 | Vancouver | Visakhapatnam | Metallurgical coal | 50000 | 51008 | 2026-09-23 | 2026-09-25 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 600 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-003 | MV IMPERIAL FORTUNE | R-09 | Vancouver | Visakhapatnam | Metallurgical coal | 50000 | 53505 | 2026-09-24 | 2026-09-26 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 600 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-004 | MV VIENNA WOOD N | R-09 | Vancouver | Visakhapatnam | Metallurgical coal | 50000 | 55768 | 2026-09-25 | 2026-09-27 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 600 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-005 | MV NORTH QUAY | R-09 | Vancouver | Visakhapatnam | Metallurgical coal | 50000 | 57016 | 2026-09-22 | 2026-09-24 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 600 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-001 | MV TS INDEX | R-10 | Hampton Roads | Paradip | Coking coal | 50000 | 38854 | 2026-09-25 | 2026-09-27 | 3 | NO | Vessel DWT 38,854 MT is below planning cargo 50,000 MT. | 730.8 | YES | FORBID (set assignment upper bound to 0) | Infeasible in Alpha because cargo exceeds vessel DWT; keep row for explicit solver filtering.
V-002 | MV LOFTY MOUNTAIN | R-10 | Hampton Roads | Paradip | Coking coal | 50000 | 51008 | 2026-09-26 | 2026-09-28 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 730.8 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-003 | MV IMPERIAL FORTUNE | R-10 | Hampton Roads | Paradip | Coking coal | 50000 | 53505 | 2026-09-27 | 2026-09-29 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 730.8 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-004 | MV VIENNA WOOD N | R-10 | Hampton Roads | Paradip | Coking coal | 50000 | 55768 | 2026-09-28 | 2026-09-30 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 730.8 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.
V-005 | MV NORTH QUAY | R-10 | Hampton Roads | Paradip | Coking coal | 50000 | 57016 | 2026-09-25 | 2026-09-27 | 3 | YES | Vessel DWT is sufficient for planning cargo. | 730.8 | YES | ALLOW (binary assignment can be considered) | Planning laycan; not a claim of current charter availability.

## TechLead_2_Handover
Item | Instruction
Input | Use Day2_Laycan_Matrix as the domain scheduling input.
Binary feasibility | If Feasible? = NO, force the corresponding vessel-route decision variable to 0.
Laycan window | For feasible rows, assignment/start timing must respect Laycan Start <= decision date <= Laycan End.
30-day horizon | Do not create assignment dates outside 05-Sep-2026 to 04-Oct-2026.
Big-M | Use the laycan window in the conditional constraints rather than hard-coding a single availability date.
Interpretation | Laycans are Alpha planning assumptions; do not describe them as live market availability.
QA | Check that no vessel below route planning cargo is assigned.

## Day2_Assumptions
ID | Assumption | Reason
D2-A01 | 30-day horizon = 05-Sep-2026 through 04-Oct-2026 | Keeps all Day 2 scheduling inputs inside one explicit Alpha horizon.
D2-A02 | Each feasible vessel-route pair receives a 3-day laycan | Simple enough for Alpha while giving MILP temporal flexibility.
D2-A03 | Route windows are staggered through September | Creates realistic scheduling competition instead of making all cargo available on one date.
D2-A04 | Vessel offsets vary laycan timing slightly | Represents different assumed readiness dates without claiming real vessel availability.
D2-A05 | DWT >= planning cargo is the hard vessel-capacity rule | Prevents physically impossible cargo assignments.
D2-A06 | Voyage duration is distance / 13 kn | Matches the Day 1 planning convention; port/weather delays are excluded.

## Day2_Summary
Metric | Value
Total vessel-route combinations | 50
Feasible combinations | 40
Infeasible combinations | 10
Planning horizon start | 2026-09-05
Planning horizon end | 2026-10-04
Laycan length | 3 days
Capacity rule | Vessel DWT >= Planning Cargo